## Risk List
Project title: Box Robot
ID | Title | Description | Responsible | Category | Indicators of occurence | Probability | Impact | Risk score | Impact x-axis | Likelihood y-axis | Preventive Measure | Corrective Measure | Success factors | Probability ' | Impact ' | Impact x-axis | Likelihood y-axis | Risk score '
R1 | Power Motor Axis X | The power of the electric motor is too low. | Mechanical engineer | Technical | The speed of the process cannot be achieved. | Possible | Major | 12 | 3.5 | 2.5 | Contact specialist for better calculation | Order new motor | The final speed is achieved | Unlikely | Moderate | 2.5 | 1.5 | 6
R2 | Processor of PLC | The calculation capacity of the PLC is too low | Electrical engineer | Technical | Crash of PLC | Remote | Critical | 5 | 4.5 | 0.5 | None
R3 | Delivery time of safety relay | Due to critical situation on the market of semi-conductors, the safety relay cannot be delivered on time | Buyer | Projectmanagement | Unable to deliver the system on time | Likely | Major | 16 | 3.5 | 3.5 | Contact the supplier to know the delivery times | Select another product | Device delivered on time | Unlikely | Minor | 1.5 | 1.5 | 4
R6 | Risk Six
R7 | Risk Seven | [7 empty] | -1 | -1 | [5 empty] | -1 | -1
R8 | Risk Eight | [7 empty] | -1 | -1 | [5 empty] | -1 | -1
R9 | Risk Nine | [7 empty] | -1 | -1 | [5 empty] | -1 | -1
R10 | Risk Ten | [7 empty] | -1 | -1 | [5 empty] | -1 | -1
R11 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R12 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R13 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R14 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R15 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R16 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R17 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R18 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R19 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R20 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R21 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R22 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R23 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R24 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R25 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R26 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R27 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R28 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R29 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R30 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R31 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R32 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R33 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R34 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R35 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R36 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R37 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R38 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R39 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R40 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R41 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R42 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R43 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R44 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R45 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R46 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R47 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R48 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R49 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
R50 | [8 empty] | -1 | -1 | [5 empty] | -1 | -1
Note on B3: Titel or short description of the risk
Note on C3: Detailes description of the risk and comments can be made here
Note on D3: Person or Organisation that is responsible for this risk resp. who will perform the defined actions
Note on E3: Category of the risk
Note on F3: How do you know the risk occured?
Note on G3: Probability of occurence of the risk: Remote: Probability of less than 10%. Unlikely: Probability between 10% and 35% Possible: Probability between 36% to 64%. Likely: Probability 65% to 90%. Certain: Probability above 90%.
Note on H3: Levels of consequence: Insignificant: Easily handled within the normal course of operations with no additional costs Minor: Some disruption within the normal functions. Manageable risk with minimum estimated cost Moderate: Immediate time/resource reallocation will be necessary with a moderate estimated cost Major: Operations are severely disrupted and significant risk of failure to part of the business is possible Critical: Significant going concerns exists with the business and the risk is classified as critical
Note on I3: Is calculated automatically (Probability * Impact)
Note on L3: Preventive action to mitigate the probability Example Risk: Building burning Measure: Build non smoking areas in critical areas.
Note on M3: Corrective action to reduce the resulting damage Example Risk: Building burning Measure: Build sprinkler systems and provide emergency exits and escape routes.
Note on N3: How will we know that this risk is successfully mitigated? Example Risk: Increase of budget Success factor: Tracking of costs and closing the project in budget
Note on O3: Probability after application of measures
Note on P3: Impact after application of measures
Note on S3: Risk score after application of measures Is calculated automatically (Probability' * Impact')

## Parameter
Probability
Remote | 1 | Probability of less than 10%.
Unlikely | 2 | Probability between 10% and 35%
Possible | 3 | Probability between 36% to 64%.
Likely | 4 | Probability 65% to 90%.
Certain | 5 | Probability above 90%.
Impact
Insignificant | 1 | Easily handled within the normal course of operations with no additional costs
Minor | 2 | Some disruption within the normal functions. Manageable risk with minimum estimated cost
Moderate | 3 | Immediate time/resource reallocation will be necessary with a moderate estimated cost
Major | 4 | Operations are severely disrupted and significant risk of failure to part of the business is possible
Critical | 5 | Significant going concerns exists with the business and the risk is classified as critical
Category
Implementation | 1
Management | 2
Market | 3
Projectmanagement | 4
Research | 5
Technical | 6
Other | 7

## Chart Template
|  | Risks | [6 empty] | Risks after measures
| Certain | Low Med | Medium | Med Hi | High | High |  | Certain | Low Med | Medium | Med Hi | High | High
Likelihood | Likely | Low | Low Med | Medium | Med Hi | High | Likelihood | Likely | Low | Low Med | Medium | Med Hi | High
| Possible | Low | Low Med | Medium | Med Hi | Med Hi |  | Possible | Low | Low Med | Medium | Med Hi | Med Hi
| Unlikely | Low | Low Med | Low Med | Medium | Med Hi |  | Unlikely | Low | Low Med | Low Med | Medium | Med Hi
| Remote | Low | Low | Low Med | Medium | Medium |  | Remote | Low | Low | Low Med | Medium | Medium
|  | Insignificant | Minor | Moderate | Major | Critical |  |  | Insignificant | Minor | Moderate | Major | Critical
|  |  |  | Impact | [6 empty] | Impact